## Sheet1
S.NO | TASK NAME | DURATION | PRECEEDING ACTIVITY
1 | LEARNING HTML | 5 HRS | -
2 | LEARING CSS | 5 HRS | 1
3 | LEARINING PHP | 10 HRS | 2
4 | PROJECT DECISION | 4 HRS | -
5 | LEARING REMAINING PHP | 10 HRS | 3
6 | SOFTWARE INSTALLATION | 5 HRS | 4
7 | DESIGNING LOGIN PAGE | 5 HRS | 5,6
8 | DESIGNING REGISTER PAGE | 5 HRS | 5,6
9 | DESIGNING HOME PAGE | 5 HRS | 5,6
10 | ER DIAGRAM | 5 HRS | 4
11 | ER DIAGRAM TO RELATION TABLE CONVERSION | 3 HRS | 10
12 | DATABASE INITIALISATION | 6 HRS | 11
13 | FORM CONNECTIVITY | 5 HRS | 7,8,9
14 | INTEGRATION AND INTEGRATION TESTING | 5 HRS | 13
15 | DEBUGGING AND ERROR TRACING | 6 HRS | 14
16 | SEARCH EINGINE DESIGNING | 4 HRS | 12
17 | HOME PAGE MODIFICATION | 6 HRS | 14
18 | CONSTRAINT DESIGNING | 6 HRS | 10
19 | SETTING PAGE OF WORKER/CLIENT | 8 HRS | 18
20 | PROFILE PAGE OF WORKER | 10 HRS | 18
21 | PROFILE PICTURE OF WORKER/CLIENT | 5 HRS | 18
22 | INTERFACE TO CONNECT WORKER AND CLIENT | 7 HRS | 12
23 | INTERFACE TO SEND MESSAGE BETWEEN WORKER AND CLIENT | 8 HRS | 12
24 | NOTIFICATION PANEL FOR CLIENT AND WORKER | 5 HRS | 23
25 | INTERFACE TO ACCEPT/REJECT CLIENT REQUEST BY WORKER TO PROVIDE SERIVCE | 4HRS | 19
26 | EXCHANGE OF DETAILS BETWEEN CLIENT AND WORKER(ADDRESS,CONTACT,INSTRUCTION,SERVICE TIME) | 4 HRS | 21
27 | INTERFACE TO CANCEL SERVICE REQUEST | 4 HRS | 22
19 | SERVICING THE REQUEST
20 | SERVICE SUCCESSFUL | 4 HRS | 23
21 | DISCONNECT CLIENT AND WORKER | 4HRS | 25
22 | REVIEW AND RATINGS | 6 HRS | 26
23 | SHARE WEBSITE WITH FRIENDS | 4 HRS | 27
24
25
26
27
28